## Username
Username | Student Name
rhrmit | Ronald Ho (s3436258)
thomasyao15 | Thomas Yao (s3832771)
antzod | Anthony Imani (s3950363)
Victoria-Needs | Victoria Needs (s3811305)
LedyLedy | Ledy (s3409664)
dyl-kh | Dylan Khan (s3916841)

## Product Backlog
Product Backlog
PBI | PBI Name | Title | Assignees | Iteration | Priority | Size | Status | Labels | DOD
1 | SRS document | Documentation - SRS document | Victoria-Needs | Sprint 0 | High | 3 | ✅ Done | Type: Task | SRS document finished
2 | Set up front end structure | Frontend - Setup frontend repository structure and libraries | Thomas | Sprint 1 | High | 3 | 🔖 To Do | Area: Frontend, Type: Task | Frontend repository structure and libraries are in the repository
3 | Database setup | Database - Create Database Model | dyl-kh | Sprint 0 | High | 5 | ✅ Done | Type: Task | Database created
4 | Project architecture | Investigate Microservices Architecture | rhrmit | Sprint 0 | High | 3 | ✅ Done | Area: Backend, Type: Task | Microservices Architecture is selected
5 | Initial SuperPrice Web App Design | Design - Initial SuperPrice Web App Design | LedyLedy | Sprint 0 | High | 5 | ✅ Done | Type: Task | SuperPrice Web App Design is done
6 | User can search product | Search - User can search product using search bar | Ronald | Sprint 1 | High | 3 | 🔖 To Do | Type: Story | User can search product using search bar
7 | Payment Page | User Interface - Payment Page | Thomas | Sprint 1 | Medium | 5 | 🔖 To Do | Type: Story | User can make payment
8 | User can browse product by category | Categorisation - User can browse product by category | Victoria | Sprint 1 | High | 3 | 🔖 To Do | Type: Story | User can browse product by category
9 | Setup backend repository structure and libraries | Backend - Setup backend repository structure and libraries | antzod | Sprint 1 | High | 3 | 🔖 To Do | Area: Backend, Type: Task | Backend repository structure and libraries are in the repository
10 | Checkout Address Page | User Interface - Checkout Address Page | Dylan | Sprint 1 | Medium | 5 | 🔖 To Do | Type: Story | User can enter address for delivery of their shopping
11 | Product Page | User Interface - Product Page | Anthony | Sprint 1 | Medium | 5 | 🔖 To Do | Type: Story | User can see the product that they select
12 | Homepage | User Interface - Homepage | Ledy | Sprint 1 | Medium | 3 | 🔖 To Do | Type: Story | Homepage is rendered
13 | Shop page | User Interface - Shop Page | Ronald | Sprint 1 | Medium | 5 | 🔖 To Do | Type: Story | User can browse products to shop
14 | Cart page | User Interface - Cart Page | Thomas | Sprint 1 | Medium | 5 | 🔖 To Do | Type: Story | User can see items in their cart
15 | User can leave a review of a supermarket | User Reviews - User can leave a review of a supermarket | antzod | Sprint 2 | Low |  | 📋 Backlog | Type: Story | User can leave a review of a supermarket
16 | User Reviews - User can leave a review of a product | User Reviews - User can leave a review of a product | Dylan | Sprint 2 | Low |  | 📋 Backlog | Type: Story | User can leave a review of a product
17 | Price Comparison - Registered users should only have products displayed within saved area | Price Comparison - Registered users should only have products displayed within saved area | Anthony | Sprint 2 | Low |  | 📋 Backlog | Type: Story | User can see products displayed within saved area
18 | Delivery - Driver can see an optimised route for deliveries | Delivery - Driver can see an optimised route for deliveries | Ledy | Sprint 2 | Low |  | 📋 Backlog | Type: Story | Driver can see an optimised route for deliveries
19 | User Interface - User can see recently viewed items | User Interface - User can see recently viewed items | Thomas | Sprint 2 | Low |  | 📋 Backlog | Type: Story | User can see recently viewed items
20 | Notifications - User can receive notifications | Notifications - User can receive notifications | Victoria | Sprint 2 | Medium |  | 📋 Backlog | Type: Story | User can receive notifications
21 | User Reviews - User can see review of products | User Reviews - User can see review of products | antzod | Sprint 2 | Low |  | 📋 Backlog | Type: Story | User can see review of products
22 | Login Page | User Interface - Login Page | Thomas | Sprint 2 | Low |  | 📋 Backlog | Type: Story | User can login
23 | Delivery | Delivery - User can choose delivery time | Victoria | Sprint 2 | Low |  | 📋 Backlog | Type: Story | User can choose delivery time

## Sprint 0
Sprint 0
PBI | PBI Name | Task ID | Title | Assignees | Iteration | Size | Status | Labels
1 | SRS document | 1.1 | Documentation - SRS document | Victoria-Needs | Sprint 0 | 3 | ✅ Done | Type: Task
|  | 1.2 | Documentation - Non Functional Requirements | dyl-kh | Sprint 0 | 3 | ✅ Done | Type: Task
|  | 1.3 | Documentation - Sprint Planning Note | LedyLedy | Sprint 0 | 1 | ✅ Done | Type: Task
|  | 1.4 | Documentation - Sprint Retro Note | thomasyao15 | Sprint 0 | 1 | ✅ Done | Type: Task
|  | 1.5 | Documentation - Test and Acceptance Criteria | antzod | Sprint 0 | 3 | ✅ Done | Type: Task
|  | 1.6 | Documentation - Functional Requirements | Victoria-Needs | Sprint 0 | 1 | ✅ Done | Type: Task
|  | 1.7 | Documentation - Use Cases | Victoria-Needs | Sprint 0 | 1 | ✅ Done | Type: Task
2 | Set up front end structure | 2.1 | Frontend - Setup frontend repository structure and libraries |  | Sprint 1 | 3 | 🔖 To Do | Area: Frontend, Type: Task
|  | 2.2 | Documentation - FE component architecture plan | thomasyao15 | Sprint 0 | 3 | ✅ Done | Type: Task
|  | 2.3 | Documentation - FE dependency planning | thomasyao15 | Sprint 0 | 3 | ✅ Done | Type: Task
3 | Database setup | 3.1 | Database - Create Database Model | dyl-kh | Sprint 0 | 5 | ✅ Done | Type: Task
|  | 3.2 | Database - Setup database | thomasyao15 | Sprint 1 | 5 | 🔖 To Do | Type: Task
4 | Project architecture | 4.1 | Investigate Microservices Architecture | rhrmit | Sprint 0 | 3 | ✅ Done | Area: Backend, Type: Task
|  | 4.2 | Documentation - System Architecture Diagram and Technologies/Frameworks | rhrmit | Sprint 0 | 3 | ✅ Done | Area: Backend, Type: Task
5 | Initial SuperPrice Web App Design | 5.1 | Design - Initial SuperPrice Web App Design | LedyLedy | Sprint 0 | 5 | ✅ Done | Type: Task
|  | 5.2 | User Interface - Clear Navigation | LedyLedy | Sprint 0 | 1 | ✅ Done | Type: Task
|  | 5.3 | User Interface - Primary features are easily identified | LedyLedy | Sprint 0 | 1 | ✅ Done | Design, Type: Task

## Sprint 1
Sprint 1
PBI | PBI Name | Task ID | Title | Assignees | Iteration | Size | Status | Labels
6 | User can search product | 6.1 | Search - User can search product using search bar | rhrmit | Sprint 1 | 3 | 🔖 To Do | Type: Story
|  | 6.2 | User Interface - Search Suggestions | thomasyao15 | Sprint 1 | 3 | 🔖 To Do | Type: Task
|  | 6.3 | Component - Search Bar | antzod | Sprint 1 | 1 | 🔖 To Do | Type: Task
|  | 6.4 | Backend - Search query | Victoria-Needs | Sprint 1 | 3 | 🔖 To Do | Type: Task
7 | Payment Page | 7.1 | User Interface - Payment Page | LedyLedy | Sprint 1 | 5 | 🔖 To Do | Type: Story
|  | 7.2 | Component - Horizontal Product Card | dyl-kh | Sprint 1 | 3 | 🔖 To Do | Type: Task
|  | 7.3 | Component - Order Summary Component | rhrmit | Sprint 1 | 3 | 🔖 To Do | Type: Task
|  | 7.4 | Backend - Processing payment query | thomasyao15 | Sprint 1 | 5 | 🔖 To Do | Type: Task
8 | User can browse product by category | 8.1 | Categorisation - User can browse product by category | antzod | Sprint 1 | 3 | 🔖 To Do | Type: Story
|  | 8.2 | Component - Filter Component | Victoria-Needs | Sprint 1 | 3 | 🔖 To Do | Type: Task
|  | 8.3 | Component - Load More Button | rhrmit | Sprint 1 | 1 | 🔖 To Do | Type: Task
|  | 8.4 | Backend - Filtering query | thomasyao15 | Sprint 1 | 3 | 🔖 To Do | Type: Task
9 | Setup backend | 9.1 | Backend - Setup backend repository structure and libraries | LedyLedy | Sprint 1 | 3 | 🔖 To Do | Area: Backend, Type: Task
|  | 9.2 | API Endpoint Set Up | dyl-kh | Sprint 1 | 3 | 🔖 To Do | Type: Task
10 | Checkout Address Page | 10.1 | User Interface - Checkout Address Page | rhrmit | Sprint 1 | 5 | 🔖 To Do | Type: Story
11 | Product Page | 11.1 | User Interface - Product Page | thomasyao15 | Sprint 1 | 5 | 🔖 To Do | Type: Story
|  | 11.2 | Component - Vertical Product Card | antzod | Sprint 1 | 3 | 🔖 To Do | Type: Task
12 | Homepage | 12.1 | User Interface - Homepage | Victoria-Needs | Sprint 1 | 3 | 🔖 To Do | Type: Story
|  | 12.2 | Component - Header | LedyLedy | Sprint 1 | 1 | 🔖 To Do | Type: Task
13 | Shop page | 13.1 | User Interface - Shop Page | dyl-kh | Sprint 1 | 5 | 🔖 To Do | Type: Story
14 | Cart page | 14.1 | User Interface - Cart Page | rhrmit | Sprint 1 | 5 | 🔖 To Do | Type: Story

## Sprint 2
Sprint 2
PBI | PBI Name | Task ID | Title | Assignees | Iteration | Size | Status | Labels
15 | User can leave a review of a supermarket | 15 | User Reviews - User can leave a review of a supermarket |  | Sprint 2 |  | 📋 Backlog | Type: Story
16 | User Reviews - User can leave a review of a product | 16 | User Reviews - User can leave a review of a product |  | Sprint 2 |  | 📋 Backlog | Type: Story
17 | Price Comparison - Registered users should only have products displayed within saved area | 17 | Price Comparison - Registered users should only have products displayed within saved area |  | Sprint 2 |  | 📋 Backlog | Type: Story
18 | Delivery - Driver can see an optimised route for deliveries | 18 | Delivery - Driver can see an optimised route for deliveries |  | Sprint 2 |  | 📋 Backlog | Type: Story
19 | User Interface - User can see recently viewed items | 19 | User Interface - User can see recently viewed items |  | Sprint 2 |  | 📋 Backlog | Type: Story
20 | Notifications - User can receive notifications | 20 | Notifications - User can receive notifications |  | Sprint 2 |  | 📋 Backlog | Type: Story
21 | User Reviews - User can see review of products | 21 | User Reviews - User can see review of products |  | Sprint 2 |  | 📋 Backlog | Type: Story
22 | Login Page | 22 | User Interface - Login Page |  | Sprint 2 |  | 📋 Backlog | Type: Story
23 | Delivery | 23.1 | Delivery - User can choose delivery time |  | Sprint 2 |  | 📋 Backlog | Type: Story
|  | 23.2 | User Interface - Checkout Shipping Page |  | Sprint 2 | 5 | 🔖 To Do | Type: Story

## GitHub ProductBacklog (hidden)
PBI | Title | URL | Assignees | Iteration | Size | Status | Labels
| Investigate Microservices Architecture | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/25 | rhrmit | Sprint 0 | 3 | ✅ Done | Area: Backend, Type: Task
| User Interface - Clear Navigation | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/18 | LedyLedy | Sprint 0 | 1 | ✅ Done | Type: Task
| Design - Initial SuperPrice Web App Design | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/24 | LedyLedy | Sprint 0 | 5 | ✅ Done | Type: Task
| User Interface - Primary features are easily identified | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/7 | LedyLedy | Sprint 0 | 1 | ✅ Done | Design, Type: Task
| Documentation - FE component architecture plan | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/28 | thomasyao15 | Sprint 0 | 3 | ✅ Done | Type: Task
| Documentation - FE dependency planning | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/29 | thomasyao15 | Sprint 0 | 3 | ✅ Done | Type: Task
| Documentation - SRS document | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/26 | Victoria-Needs | Sprint 0 | 3 | ✅ Done | Type: Task
| Database - Create Database Model | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/30 | dyl-kh | Sprint 0 | 5 | ✅ Done | Type: Task
| Documentation - Non Functional Requirements | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/27 | dyl-kh | Sprint 0 | 3 | ✅ Done | Type: Task
| Documentation - Sprint Planning Note | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/38 | LedyLedy | Sprint 0 | 1 | ✅ Done | Type: Task
| Documentation - Sprint Retro Note | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/39 | thomasyao15 | Sprint 0 | 1 | ✅ Done | Type: Task
| Documentation - Test and Acceptance Criteria | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/40 | antzod | Sprint 0 | 3 | ✅ Done | Type: Task
| Documentation - Functional Requirements | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/48 | Victoria-Needs | Sprint 0 | 1 | ✅ Done | Type: Task
| Documentation - Use Cases | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/49 | Victoria-Needs | Sprint 0 | 1 | ✅ Done | Type: Task
| Documentation - System Architecture Diagram and Technologies/Frameworks | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/50 | rhrmit | Sprint 0 | 3 | ✅ Done | Area: Backend, Type: Task
| Frontend - Setup frontend repository structure and libraries | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/12 |  | Sprint 1 | 3 | 🔖 To Do | Area: Frontend, Type: Task
| User Interface - Search Suggestions | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/19 |  | Sprint 1 | 3 | 🔖 To Do | Type: Story
| Database - Setup database | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/23 | thomasyao15 | Sprint 1 | 5 | 🔖 To Do | Type: Task
| API Endpoint Set Up | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/22 | rhrmit | Sprint 1 | 3 | 🔖 To Do | Type: Task
| User Interface - Payment Page | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/36 |  | Sprint 1 | 5 | 🔖 To Do | Type: Story
| User Interface - Checkout Address Page | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/33 |  | Sprint 1 | 5 | 🔖 To Do | Type: Story
| User Interface - Shop Page | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/32 |  | Sprint 1 | 5 | 🔖 To Do | Type: Story
| User Interface - Checkout Shipping Page | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/35 |  | Sprint 1 | 5 | 🔖 To Do | Type: Story
| User Interface - Product Page | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/34 |  | Sprint 1 | 5 | 🔖 To Do | Type: Story
| User Interface - Homepage | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/31 |  | Sprint 1 | 3 | 🔖 To Do | Type: Story
| Categorisation - User can browse product by category | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/5 |  | Sprint 1 | 3 | 🔖 To Do | Type: Story
| Search - User can search product using search bar | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/4 |  | Sprint 1 | 3 | 🔖 To Do | Type: Story
| Backend - Setup backend repository structure and libraries | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/13 | antzod | Sprint 1 | 3 | 🔖 To Do | Area: Backend, Type: Task
| Component - Header | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/41 |  | Sprint 1 | 1 | 🔖 To Do | Type: Task
| Component - Vertical Product Card | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/42 |  | Sprint 1 | 3 | 🔖 To Do | Type: Task
| Component - Filter Component | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/43 |  | Sprint 1 | 3 | 🔖 To Do | Type: Task
| Component - Load More Button | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/44 |  | Sprint 1 | 1 | 🔖 To Do | Type: Task
| Component - Horizontal Product Card | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/45 |  | Sprint 1 | 3 | 🔖 To Do | Type: Task
| Component - Order Summary Component | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/46 |  | Sprint 1 | 3 | 🔖 To Do | Type: Task
| Component - Search Bar | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/47 |  | Sprint 1 | 1 | 🔖 To Do | Type: Task
| User Interface - Login Page | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/37 |  | Sprint 2 |  | 📋 Backlog | Type: Story
| User Reviews - User can leave a review of a supermarket | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/17 |  | Sprint 2 |  | 📋 Backlog | Type: Story
| Price Comparison - Registered users should only have products displayed within saved area | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/16 |  | Sprint 2 |  | 📋 Backlog | Type: Story
| Delivery - Driver can see an optimised route for deliveries | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/11 |  | Sprint 2 |  | 📋 Backlog | Type: Story
| User Reviews - User can leave a review of a product | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/10 |  | Sprint 2 |  | 📋 Backlog | Type: Story
| Delivery - User can choose delivery time | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/9 |  | Sprint 2 |  | 📋 Backlog | Type: Story
| User Interface - User can see recently viewed items | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/8 |  | Sprint 2 |  | 📋 Backlog | Type: Story
| Notifications - User can receive notifications | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/3 |  | Sprint 2 |  | 📋 Backlog | Type: Story
| User Reviews - User can see review of products | https://github.com/cosc2299-sept-2023/team-project-group-p8-01/issues/2 |  | Sprint 2 |  | 📋 Backlog | Type: Story